## Function Points
UC Comment on Recipe		RET	DET	FTR		Count	Resulting Complexity
User Input			2	1		1	Low
User Output			3	1		2	Low
User Inquiries			1	1		1	Low
Internal Logical Files		1	3			2	Low
External Interface Files		0	0			0	Low
Function Points	27.72

UC Find Ingredients		RET	DET	FTR		Count	Resulting Complexity
User Input			1	1		1	Low
User Output			1	2		1	Low
User Inquiries			1	1		1	Low
Internal Logical Files		3	5			2	Low
External Interface Files		0	0			0	Low
Function Points	25.68

UC Find Recipes		RET	DET	FTR		Count	Resulting Complexity
User Input			3	4		2	Average
User Output			1	2		1	Low
User Inquiries			1	1		1	Low
Internal Logical Files		2	7			5	Low
External Interface Files		0	0			0	Low
Function Points	53.5

UC Manage Ingredient Inventory		RET	DET	FTR		Count	Resulting Complexity
User Input			3	1		3	Low
User Output			0	0		0	Low
User Inquiries			0	0		1	Low
Internal Logical Files		1	5			2	Low
External Interface Files		0	0			0	Low
Function Points	27.3

UC Manage Saved Recipes		RET	DET	FTR		Count	Resulting Complexity
User Input			6	1		3	Low
User Output			6	2		1	Average
User Inquiries			1	1		1	Low
Internal Logical Files		5	9			3	Low
External Interface Files		0	0			0	Low
Function Points	37

## Diagrams
Use Case		Time Spent / Estimation (h)	FP Done	FP Upcoming
Find Ingredients		13.5	25.68
Find Recipes		18.5	53.5
Manage Ingredient Inventory		10.9851301115242		27.3
Manage Saved Recipes		14.5910780669145		37
Comment on Recipe		11.1412639405204		27.72
Diagram Origin		0	0
Total			79.18	92.02
Time (h)
FP
f(x)= 2.69x-2.25